## KITSUNE FM TVT_2101
BIRDS 5 FM TVT Shift Schedule
Thermal & STR |  |  | Oshiro | Ofosu | Otani | Victor | Jeje
Bus & Mission operation |  |  | Keenan | Derrick | Otani | Timothy | Shoma
|  |  | ISAS | Bonny | Kamitani | Jeje
GS Operation |  |  | Ramson | Edgar
Date |  | Wednesday, Feb 2, 2022 | Thursday, Feb 3, 2022 |  |  | Friday, Feb 4, 2022 |  |  | Saturday, Feb 5, 2022
Teams |  | Structure Team assembly | Thermal & STR | Bus & Mission Operation | Ground station Operation | Thermal & STR | Bus & Mission Operation | Ground station Operation | Thermal & STR | Bus & Mission Operation | Ground station Operation
Time | 9:00-21:00 | Oshiro, Victor, Fahd, Jeje | Ofosu | Keenan | Ramson | Ofosu | Keenan | Ramson | Ofosu | Keenan | Ramson
|  |  | Victor | Derrick | Edgar | Victor | Kamitani | Edgar | Victor | Timothy | Edgar
|  |  |  | ISAS | Timothy |  | ISAS |  |  | Shoma
| 21:00-9:00 | Oshiro, Victor, Fahd, Jeje | Oshiro | Otani | Edgar | Oshiro | Otani | Edgar | Oshiro | Otani | Edgar
|  |  | Jeje | Shoma | Ramson | Fahd | Jeje | Ramson |  | Bonny | Ramson
|  |  |  | Bonny |  |  | Derrick |  |  | Kamitani
Activity |  | Set up | Small chamber : 2U Pett chamber : 1U(No.1) |  |  | Small chamber : 2U → 1U(No.2) Pett chamber : 1U(No.1) →1U(No.3)
Projected LN2 consumption rate | Remaining LN2
Rate
BIRDS 5 Structure Assembly Practice using EM
Date |  | Wednesday, Feb 2, 2022 | Thursday, Feb 3, 2022 |  |  | Friday, Feb 4, 2022 |  |  | Saturday, Feb 5, 2022 |  |  | Sunday, Feb 6, 2022 | Sunday, Feb 7, 2022
Teams |  | STR team for TVT preparation | STR | Trainee |  | STR | Trainee |  | STR | Trainee
Time | 10:00-12:00 | Spare | Fahd | Bonny | Shoma | Victor | Timothy | Jeje | Victor | Spare | Spare | Final assembly for FM Vibration
| 13:00-15:00 | Spare | Oshiro | Otani | Kamitani | Fahd | Keenan | Ramson | Oshiro | Spare | Spare
| 15:00-17:00 | Spare | Victor | Derrick | Edgar |  |  |  | Fahd | Spare | Spare